## Product Backlog
ID | Difficulty | As a/an | I want to… | so that… | Notes | Priority | Status
17 | 5 | administrator | add a new client to the system, along with their information | so that I can quickly sign up clients during meetings | Maintain a dashboard/panel for these kinds of administrator tasks and email the client with their username and randomly generator password. | required | done
18 | 2 | administrator | modify/update client details, by clicking on the client's name wherever it appears in the application | I can perform this task without interrupting my work flow any more than necessary |  | required | done
30 | 13 | administrator | see a calendar view of any month, with events listed in each day | I can have an overview of events coming up and manage my time wisely |  |  | done
31 | 13 | administrator | click on any day in the calendar view to see the schedule for that day, which rooms are booked, etc… | I can add/modify/delete events
22 | 8 | administrator | add/modify room bookings manually | I can manage events for all my clients | I should be able to confirm or deny any tentative booking, and add or delete any booking | required
21 | 2 | administrator | confirm or deny tentative bookings on the calendar page without leaving the calendar view | I can quickly go through all the requests
32 | 8 | administrator | make recurring bookings | I don't have to manually add many meetings for frequent clients | e.g., every Friday at 2-4pm for the next 4 weeks
24 | 3 | administrator | accept all pending requests that have no timetable conflicts | I have more time for other tasks in the office
19 | 1 | administrator | distinguish between various types of events in the calendar | I can have a good general overview of the schedule | Requested, conflicting and confirmed room bookings should be different colours
26 | 5 | administrator | set my email address on a user-settings page, along with some notification preferences | I can get automatic email notifications for certain events
13 | 1 | front-desk staff | easily access all the same information as an administrator | I can provide front-desk services to clients in person and over the phone | I should be able to see upcoming events and their status (requested, confirmed, etc…), and access client infformation.
14 | 1 | front-desk staff | make tentative (i.e., requested) room-bookings on behalf of any client | clients can make bookings without having to contact an administrator | I should not be able to confirm room bookings though, since that decision is up to an administrator
15 | 1 | front-desk staff | cancel events | I can help clients reschedule
1 | 0 | client | request room bookings for my events online | I do not need to go to, or contact, the Storefront to make my services available to the community | Just ensure the client can login and book events | required
2 | 5 | client | see a map of the Storefront's bookable rooms | so that I can best decide which room is appropriate for my event | I should be able to see the room capacity, and any other amenities (e.g., a desktop computer) that come with it
3 | 1 | client | make recurring booking requests | I do not need to manually book a repetitive schedule |  | required
5 | 3 | client | be notified by email whenever one of my booking requests is confirmed | I can be sure my place is reserved
6 | 1 | client | be notified by email whenever one of my booking requests is cancelled or denied | I can make other arrangements
7 | 3 | client | see a table of which rooms are availablee at which times on a given day | I can plan my events accordingly
8 | 0 | client | have my username and password stored in my computer | I don't have to type a username and password everytime I login to the application | This happens automatically depending on the browser you use |  | invalid
9 | 1 | client | I want to be able ot change my profile information (e.g., contact information) on a user-settings page | I don't have to inform an administrator whenever my information changes
11 | 1 | public user | see all upcoming events for the Storefront in one place | I can easily spot an event that might interest me | Just ensure that the public have access to view the calendar and nothing else | required
12 | 1 | public user | see detailed information about events that I am interested in | I can plan my schedule properly
4 | 2 | client | I want to notify the storefront management about materials that I need for my events | the Storefront management can prepare them for me
10 | 13 | client | I want my subordinates to be able to book events | I can delegate my tasks | Only I should be able to confirm their booking requsest for an administrator to approve
16 | 2 | front-desk staff | I want to be able to add/remove clients form a waiting list | I can manage booking conflicts
20 | 2 | administrator | I need to be able to distinguish booking times that have a waiting queue | I can manage booking conflicts
23 | 13 | administrator | I need to be able to move scheduled events in the calendar view using a drag-and-drop approach | I can quickly reschedule room bookings | This was completed as it provides a starting point for adding/modifying/deleting events |  | done
25 | 13 | administrator | I need to be able to see a map of the building and its rooms that identifies which rooms are currently occupied at that moment | I can manage the building more effectively

## Sprint Backlog
Row | User Story | ID | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
5 | User Story #31 As a/an administrator, I want click on any day in the calendar view to see the schedule for that day, which rooms are booked, etc…, so that I can add/modify/delete events | 31.1 | Implement the hook for the calendar that redirects the main page to the day view when a user clicks on a day
|  | 31.2 | Design the day view in a rough photoshop design style
|  | 31.3 | Implement the design from 31.2 in html and css
|  | 31.4 | Implement the functionality that you can quickly add events in the calendar by clicking on a time slot or clicking and dragging
|  | 31.5 | When a user clicks on an event in a day/week/month view, it should take them to a page that will allow them to edit the event
6 | User Story #22 As a/an administrator, I want add/modify room bookings manually, so that I can manage events for all my clients | 22.1 | Design the add/modify event booking page
|  | 22.2 | Create the design in html/css without working functionality
|  | 22.3 | Implement the API for the adding/updating/deleting an event in the controller `main.php`
|  | 22.4 | Implement the booking class and model for it to be able to have all the features in the design from 22.1
|  | 22.5 | Create manual test cases
7 | User Story #21 As a/an administrator, I want confirm or deny tentative bookings on the calendar page without leaving the calendar view, so that I can quickly go through all the requests |  | Code the…
Design the…
Talk to Jaime about…
Design the UI
Create manual test cases
8 | User Story #32 As a/an administrator, I want make recurring bookings, so that I don't have to manually add many meetings for frequent clients |  | Code the…
Design the…
Talk to Jaime about…
Design the UI
Create manual test cases
9 | User Story #24 As a/an administrator, I want accept all pending requests that have no timetable conflicts, so that I have more time for other tasks in the office |  | Code the…
Design the…
Talk to Jaime about…
Design the UI
Create manual test cases
10 | User Story #19 As a/an administrator, I want distinguish between various types of events in the calendar, so that I can have a good general overview of the schedule |  | Code the…
Design the…
Talk to Jaime about…
Design the UI
Create manual test cases
11 | User Story #26 As a/an administrator, I want set my email address on a user-settings page, along with some notification preferences, so that I can get automatic email notifications for certain events |  | Code the…
Design the…
Talk to Jaime about…
Design the UI
Create manual test cases